## Sheet1
Quintom/Wasabi App
Task | Estimated Hours
Duplicati Code understanding | 16
Login/signup and Roles
Database design and project architecture | 16
UI design and implementation | 8
Api design and integration for 3rd party like google | 16
Backend Coding C# | 16
User Dashboard
Database design with SP for Get data | 16
UI design and implementation | 8
Api's for get data as JSON | 8
Backend Coding C# | 16
Admin Dashboard
Database design with SP for Get data | 16
UI design and implementation | 8
Api's for get data as JSON | 8
Backend Coding C# | 16
User Management
Database design with SP for Get data | 16
UI design and implementation | 8
Api's for get data as JSON | 8
Backend Coding C# | 16
Settings | Need to discused
S3 bucket Api integration with User dashboard | 16
For this we can use duplicati api or we can directly access s3 bucket using Api